2021 ANA Western Region’s Workbook for

Project Planning and Development Training

By using this template and completing the following prompts, you will have created a strategy that will help you to move forward in your project planning process.

Work through each section in this workbook to involve your community in an effective planning process and develop a project that they wish to see succeed. As you progress, you will help to build a planning team and community capacity to complete the activities and numbered document pages. Remove the activity pages to display your final plan. Then come back to this plan and make revisions as the team learns more about potential project design options. It is a working document as you and your steering committee pursue a final project idea.

**Instructions:** Activities are included to help you and your team brainstorm before completing each numbered section. Conceptualize strong community connections to use in the process before developing the Products of the Planning Process (project design elements, like the community’s conditions and desired solutions).

*Do not produce design elements until you involve the community in a planning process!*

1. **Tribal and/or Organizational Background** – Provide information about your organization and the values and aspirations of your organization.
2. **Community Connections** – First, describe the community, including its location, demographics, and other defining features. Then inventory the community subsets (elders, youth, single parent families, etc.) in your overall population. Finally, describe the people and partners you can tap into as you move forward.
3. **Community Engagement Outreach Plan** – Consider how to build rapport and recruit community members to secure their input. Then draft a plan to move forward using methods of community engagement.
4. **Steering Committee** – After you’ve conducted outreach, note which community members are responsive, are representative of the community, and can commit to ongoing meetings while contributing to the planning process. Work together to identify a clear mission for the committee as well as a time, date and location for meeting. The frequency may differ depending on workload, but plan to meet weekly in the beginning and at least quarterly once project implementation begins.

***STOP!*** *Do you have a steering committee established? Get a committee together before progressing.*

1. **Surveys** – Surveys can be used to collect input on many different topics. As a team, identify the information you need to collect, the survey methods you intend to use, and record the results of your efforts.
2. **Community Meetings** – With your steering committee, work to identify existing meetings that you can tap into to gather a variety of community input. If there are no existing meetings, plan to host your own.
3. **Focus Groups** – Focus groups delve deeper into one specific topic that resulted from your general community information gathering. Identify who will participate and plan for an in-depth discussion.
4. **Key Informant Interviews** – Plan to speak one-on-one with community members who have personal experience with the issues you’ve uncovered. Identify who you will speak with and how you intend to encourage them to open up.
5. **Secondary Sources/Annotated Bibliography** – Your primary research will result in several claims being made about the personal experiences of community members. Support these claims with secondary sources.

*The Community Readiness Assessment Activity does not include a numbered section. Please see the notes*.

1. **Next Steps** – reflect on the process thus far, follow up on any incomplete activities, and identify next steps before you move on to identifying the project design elements outlined in ANA’s PPD Manual.
2. Tribal and/or Organizational Background

Date:

Name:

Address:

Contact:

Mission Statement:

Vision Statement:

Contemporary and/or Traditional Values:

Activity - Community Connection Mapping

Fill in the map below, expand on it, or use a separate piece of paper to get all of your connections down. Consider who you know, who they know, and who is missing. Ask yourself if you have representatives from every area of the community, including: elders, youth, staff, professionals, veterans, business owners, artisans, language speakers, and other knowledge holders. Also include partners and existing programs, such as: Head Start, TANF, IHS, tribal colleges, local businesses or nonprofits, libraries, or any other existing program or service.

2. Community Connections

Description of Community (including size, location, demographics, etc.):

Potential People and Partners:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name | Affiliation | Skill/Expertise | Contact | Potential Contribution |
| Ex: Mrs. Begay | Elder, Veteran | First Language Speaker | (123) 456-7890 | Steering Committee Member |
| Ex: Head Start | Youth, Teachers | Classroom Curriculum | (987) 654-3210 | Youth Survey Respondents |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Activity – Community Outreach

Consider how you will network with those people and partners as well as build a rapport with new connections. Identify the methods you can use to engage with each and every individual, such as through upcoming events, personal introductions, word-of-mouth, mail, newsletters, public media announcements, and so on. Use this space to think through your methods and what will be needed to accomplish these methods.

1. Does your community have a community calendar of events (virtual or in-person)? \_\_\_Yes \_\_\_No
   1. If yes, what events can you attend or speak at to garner community interest:
2. Does your community have a radio and/or television station? \_\_\_Yes \_\_\_No
   1. If yes, what will you need to do to tap into this media to recruit others to join a conversation:
3. Does your community/organization have a newsletter, website, or other publication? \_\_\_Yes \_\_\_No
   1. If yes, how will you advertise your interest in bringing the community to the table:
4. Do you or your community/organization have social media accounts? \_\_\_Yes \_\_\_No
   1. If yes, who is your audience and how will you engage them in the conversation:
5. Do you have personal connections with a network of their own? \_\_\_Yes \_\_\_No
   1. If yes, who will you reach out to, how will you do so, and what is needed to encourage them to introduce you to their network:
6. What other types of outreach will you consider and how will you use it?

\*\*Now prioritize these methods and, on the next page, consider what you tap into first

3. Community Engagement Outreach Plan

Our prioritized outreach methods include:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Type | Key Staff | Message | Goal | Timeline |
| Ex: Council Mtg. | Program Mgr. | Announce intent to collect community input | Council Approval and Support | Dec. 10th |
| Ex: Facebook | Media Tech | Announce planning and follow up with people liking the post | At least 15 likes with individual names | Now – Nov 30th |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Results of our outreach (full record held in secure \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_):

|  |  |  |  |
| --- | --- | --- | --- |
| Individual | Affiliation | Availability | Assignment |
| Ex: Mrs. Begay | Elder, Veteran | Only available on weekends | Virtual Steering Committee Member |
| Ex: Johnny Cash | Youth | During after school program | Survey Respondent, future volunteer |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Activity – Steering Committee

A steering committee is crucial to ensuring that you maintain community input throughout your planning process. Your steering committee will be composed of representatives of the larger population, will have their own network to tap into, and will be responsible for completing assigned planning tasks. You’ll need to select someone responsible who also has the availability and capability to contribute to the project planning process. Make use of those you identified above to begin structuring a well-rounded committee. List those you know who could represent these community areas or think of your own most relevant areas (overlap is okay, but be sure to have a variety from each area):

STAFF: ELDERS:

YOUTH (or PARENT REPRESENTATIVES): BUSINESS OWNERS:

LANGUAGE SPEAKERS: CULTURAL KNOWLEDGE HOLDERS:

FUNCTIONAL LEADERS: ACTIVE VOLUNTEERS:

VETERANS: ARTISANS:

COLLEGE STUDENTS/RECENT GRADS: HOMEOWNERS:

PARTNER ORGANIZATIONS: YOUR IDENTIFIED AREA:

NOTE: A steering committee should be large enough to capture a snapshot of community interests, but still be small enough manage. The next step is to narrow this list to just 8-10 people who can commit to participating.

4. Steering Committee

Steering Committee Roster – Confirmed Members:

|  |  |  |  |
| --- | --- | --- | --- |
| Individual | Affiliation | Contact Information | Committee Task Group/Assignments |
| Ex: Mrs. Begay | Elder, Veteran | (123) 456 -7890 elder@gmail.com | Minutes Keeper, Key Informant Interviews |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Steering Committee Mission Statement:

Meeting Information:

|  |  |  |
| --- | --- | --- |
| Day/Date | Time | Location |
| Ex: First Saturday of each month | 11am – 1pm | ZOOM Meeting: https://zoom.us/joinlink |
|  |  |  |

Activity – Surveys

Surveys offer a straightforward, standardized, and often anonymous method for community members to provide their input. These can be paper surveys or electronic. They can be conducted in-person, over-the-phone, by mail, or by email. Questions can include closed-ended questions that limit responses to multiple choice or yes/no answers or open-ended questions that allow survey respondents to fill in the blank and get creative. There is no limit to the type or number of questions, but we do have a few tips. First, people are often bombarded with surveys for one thing or another, so consider when you might use one and when another planning method might work better. Additionally, you will likely want to keep initial surveys to a short 10 questions or less to start. That way, survey takers don’t feel overwhelmed. Ask them if they are interested in a follow up survey that could be longer in length. And be sure your questions are to the point without leading the survey taker to respond in a certain way – for the most honest input, keep your questions unbiased.

Finally, before you develop a survey, work with your steering committee to determine the following:

1. What do you hope to learn from this survey?
2. What information do you need to collect from community respondents in order to learn this?
3. Should respondents remain anonymous? \_\_\_Yes \_\_\_No
   1. If yes, what tool will you use to collect this information?
   2. If no, how will you encourage honest and open opinions?
4. Who is the target audience? Is it a sub-set of the general community? \_\_\_Yes \_\_\_No
   1. If yes, describe their demographics:
5. How will you reach your target audience and encourage them to respond (ex. incentives)?
6. How many people will you engage, and how many responses do you need to decently represent this target audience?
7. How long will it take to conduct this survey (note: include time for delivery, response, and return)?
8. Who will compile the survey results and how (ex. automatically generated by survey monkey, manually in a spreadsheet based on surveys returned to a drop box location)?
9. Who will be responsible for analyzing the results?
10. How will the results be used?

5. Surveys Plan

Our prioritized surveys include:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Audience | Key Staff | Research Aim | Survey Type/Size | Timeline |
| Ex: High Schoolers | Steering Com. Member (Teacher at the School) | Biggest risk factors to youth in our high school? | -Anonymous in-class paper surveys  -200 youth (~100 responses) | Sept 1 – Oct 15 |
| Ex: Parents | Steering Com. Member  (Parent of 18-yr old) | Biggest risk factors to your high school-aged child? | -Anonymous electronic survey  -115 parents (~50 responses) | Sept 1 – Oct 15 |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Summary of data collected (full record held in secure \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_):

|  |  |  |  |
| --- | --- | --- | --- |
| Survey | Date | Summary of Results | Follow Up Tasks |
| Ex: High Schoolers | Oct 15 | -153 of 200 students responded  -85% of responses mentioned student concerns for safe spaces after school | -Attend community meetings to talk to students directly about safe spaces |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Activity – Community Meetings

Community meetings are an easy way to gather community input, quickly. And piggybacking on an existing event is one of the best ways to do this. These may be formal gatherings such as tribal council meetings, or informal ones like potlucks or celebrations. They may be held in-person or virtually. But if there are no events, you will need to put in additional effort to host one yourselves.

You can also conduct your research formally or informally in these settings. Determine with your steering committee if you need to be formally added to a meeting agenda. If so, you may need to reach out to your tribal administrator or board secretary well in advance of the meeting. Or, you can informally poll event attendees by asking questions and encouraging discussion. No matter your method, be sure to take detailed notes on the concerns raised that can be shared with and analyzed by the steering committee.

Finally, come to consensus with your steering committee on the information you need to discover at these meetings. In the early stages of project planning, you may be looking for an overall understanding of challenges faced by your community. Then you may want to conduct a community readiness assessment. And later, when you’ve narrowed the scope of your project to top priority ideas, you’ll need to go back to the community and discover their preferred solutions. For now, consider the following planning steps before you begin your process.

In the previous outreach activity, you were asked if the community has an events schedule (virtual or in-person).

1. If yes, what events will you attend or speak at (including dates and times)?
   1. How will you make this happen (ex. request time in the agenda, host a booth, bring a dish to share)?
2. If no, what event will you host (including types, dates, and times)?
   1. What will you do to make this happen (ex. reserve a meeting space, borrow a friend’s kitchen)?
   2. How will you encourage attendance and participation (ex. outreach methods, incentives)?
3. How will you capture the variety of community input being shared?

6. Community Meetings Plan

Our prioritized meetings include:

|  |  |  |  |
| --- | --- | --- | --- |
| Type | Key Staff | Research Aim | Timeline |
| Ex: Family gathering | 5 steering committee members | What long-term community goals exist in our community? | April 4th |
| Ex: Powwow | 2 steering committee members | Do attendees know about rising crime rates and the services the Tribe currently provides? | May 15th |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Summary of collected data (full record held in secure \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_):

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Individual | Event | Date | Testimony/Insight | Contact |
| Ex: Anita Berry | Powwow | May 15th | Didn’t know crime rates were so high. Thought the Police Dept. had an at-risk youth program. | (222) 555 - 0000 |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Summary of data collected, continued (full record held in secure \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_):

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Individual | Event | Date | Testimony/Insight | Contact |
| Ex: Anita Berry | Powwow | May 15th | Didn’t know crime rates were so high. Thought the Police Dept. had an at-risk youth program. | (222) 555 - 0000 |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Activity – Focus Groups

A focus group is comprised of a small number of community members who represent the larger target audience. They should be those people who have personal experience with the issues they are coming together to discuss. Focus group participants should not include your steering committee members. Where community meetings and surveys aim to generate consensus, a focus group can be used to pick specific issues apart and identify differences of opinions. Unbiased and open-ended questions leave room for discussion. However, you may need to plan an ice breaker, anonymous polling, or other introduction to get the conversation started.

1. What specific issue, topic, or concern will you delve into through the use of a focus group?
2. What outreach methods will you use to identify community representatives who also have first hand experience with that issue and are willing to join a focus group?
3. How will you recruit and engage participants (ex: food, incentives, or accommodations like childcare)?
4. Where will you host the focus group? And how much time is needed to generate a discussion?
5. How will you get the conversation flowing?
   1. What ice breaker is needed to allow others to feel comfortable sharing their opinions?
   2. What ground rules will you establish to ensure everyone’s opinions are voiced, heard and respected?
   3. What questions will you ask in order to pick apart the topic at hand?

6. Focus Group Plan

Our prioritized focus groups include:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Audience | Key Staff | Research Aim | Type/Size/Duration | Date |
| Ex: High Schoolers | Steering Com. Member (Teacher at the School) | What would youth like to see in an after-school safe space? | -Zoom Gathering w/ Prize Drawing  -16 youth: 2 different groups of 8  -2 Hours: 1 morning, 1 afternoon | Nov 1 |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Summary of data collected (full record held in secure \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_):

|  |  |  |  |
| --- | --- | --- | --- |
| Survey | Date | Summary of Results | Follow Up Tasks |
| Ex: High Schoolers | Nov 1 | -3 students felt afraid to walk home alone after school  -5 students wanted to learn a business-related skill  -All 16 students wanted homework help | -Interview teachers to determine willingness, interest, and insight into students |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Activity – Key Informant Interviews

Those who are affected by the issues your community faces are considered Key Informants. They can inform you of what every day life is like while dealing with that issue. They can provide insight that you may not have considered before. This will be crucial to designing a project that fits the needs of the community and the very people who are expected to participate in the project. They also build trust and rapport with those future participants. But getting someone to speak openly about what very well may be a sensitive topic is no easy task. Work with your steering committee to plan best practices that suit the culture of the community.

1. What specific issue, topic, or concern will you ask a Key Informant to provide insight on?
2. What outreach methods will you use to identify community representatives who also have first hand experience with that issue and are willing to speak openly with you, one-on-one?
3. How will you recruit and engage participants (ex: reassurances, anonymity, incentives)?
4. How will you speak with them (in-person, by phone, by email)? And how much time will you plan for?
5. How will you build rapport and encourage the participant to open up?
6. What questions will you ask to get started (then, allow for the conversation to flow naturally)?

7. Key Informant Interview Plan

Our prioritized key informants include:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Audience | Key Staff | Research Aim | Type/ Duration | Date |
| Ex: Mr. Echohawk (Teacher) | Steering Committee Member (Elder) | What homework do youth struggle with and why? | -Phone Call, at least 1 hour | Nov 10 |
| Ex: Johnny Cash  (High schooler) | Steering Com. Member (Business Owner) | What interests you about learning business skills? | -Meeting in person, 1 hour | Nov 15 |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Summary of data collected (full record held in secure \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_):

|  |  |  |  |
| --- | --- | --- | --- |
| Survey | Date | Summary of Results | Follow Up Tasks |
| Ex: Mr. Echohawk | Nov 10 | -Students can’t grasp concepts at the pace the school expects them to, and classes are only 50 minutes long  -Testing is stressful, youth do better in group projects | -Research local and regional secondary data to support claims |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Activity – Secondary Sources

Once the steering committee has collected, compiled and analyzed the results of their primary research (meeting minutes, survey results, focus group discussions, and interview testimonies); begin supporting the claims being made by making observations at the local, regional, and state level. You can tap into existing research and studies conducted by other Tribal agencies, such as IHS or TANF, by colleges or libraries, and by state agencies or other parties of interest. The types of claims being made by your community (such as high crime rates or poor housing quality) will help to determine where to look for supporting data. You can also use this information to make comparisons between your community and other similar communities.

1. What claims have been made by your community about issues, topics of interest, or concerns?
2. What secondary resources may hold more information regarding these claims?
3. How will you obtain infromation from these secondary sources (ex. gain permission from TANF to review records)?
4. Who is responsible for conducting this research?

8. Annotated Bibliography

Our secondary sources:

|  |  |  |  |
| --- | --- | --- | --- |
| Source | Citation | Annotation | Page Number |
| Ex: JStor – Online Database | Smith, Jane. “The Article About Education in This Specific Region.” *An Important Journal* 12.1 (2017). | Students in ABC community who work together learn more quickly and are XX times more likely to attend post-graduate education compared with their counterparts in XYZ county up the road. This demonstrates that groupwork is an important aspect of ABC culture. However, schools across the region are less likely to emphasize team work over performance on standardized tests in XX % of classrooms due to increased demands on time. | 112-113 |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Activity – Community Readiness

The data collected thus far will be extremely useful in planning a project that the community wants and needs. But is the community ready to address the issues you’ve identified throughout this planning process? It is one thing to recognize that an issue exists. It is wholly another to be ready, willing and able to make significant changes. Like the old adage, “You can lead a horse to water, but you can’t make it drink.” The scope of project is dependent upon your community’s stage of readiness. Your steering committee may recognize that there are high rates of crime, and the youth may say that they need safe spaces after school. But if parents aren’t aware of how their children feel, then they may not support their kids’ participation. Parent’s may even be in denial. As a project planner, you need to gauge the receptiveness of the community to implement a community-based project, or there may be very little interest at all. A project without community support will not succeed!

NOTE: The following is based on more extensive “Community Readiness for Community Change” training materials developed by the Tri-Ethnic Center for Prevention Research at Colorado State University.

In this Community Readiness Model, the steps taken to assess community readiness are:

1. Identify and clearly define your issue.

2. Identify and clearly define and delineate your community.

3. Prepare your interview questions.

4. Choose your key respondents.

5. Conduct and transcribe your interviews.

6. Score the interviews.

7. Calculate your average dimension scores.

Much of this is similar to the planning process you have worked through, thus far. However, the questions posed to community members will be more pointed and ask for more specific examples – avoiding personal opinions as much as possible. Responses will be recorded and scored to determine where in the following Model the community falls. The community may be anywhere on this spectrum, moving up or down as time goes on:

Community Ownership – Most community members have detailed knowledge of the issue and existing resources. They are actively involved, as is leadership. Funding is secured and efforts are ongoing.

Expansion/Confirmation – Most community members have knowledge and are supportive. Leadership plays a role, and a considerable portion of the budget is allocated to the effort. Funding is likely ongoing.

Stabilization – Most community members have more than basic knowledge and the attitude is “We have taken responsibility” for the issue. Leadership is working on viability and funding has been allocated.

Initiation – Most community members have at least basic knowledge and the attitude is “This is our responsibility.” Leadership is working on planning and resources are being obtained.

Preparation – Most community members have heard about the issue and local efforts, and they are concerned. Leadership is working to develop new efforts. Some funding and resources are identified.

Preplanning – Some community members have heard about the issue, but little is known. Leadership has acknowledged that there is a concern. There are limited resources available or identified.

Vague Awareness – Few community members have heard of the issue. There is little leadership action.

Denial/Resistance – The community believes this is not an issue and does not support diverting resources.

No Awareness – There is no knowledge in the community, and leadership has no concerns.

Example: Let’s see what this may look like for a community experiencing high rates of crime and at-risk youth.

|  |  |  |  |
| --- | --- | --- | --- |
| Stage | Leadership | Parents | Youth |
| No Awareness | “Kids will be kids.” | “My child is fine.” | “It is what it is.” |
| Denial/Resistance | “There’s nothing we can do.” | “My child isn’t the problem.” | “Everyone else is doing it.” |
| Vague Awareness | “Something should probably be done, but what?” | “Someone should fix this.” | “What else is there to do?” |
| Preplanning | “This is important.” | “What can I do?” | “I want other options.” |
| Preparation | “I’ll meet with funders.” | “I’ll bring this to leadership.” | “I’ll tell the teacher.” |
| Initiation | “This is our responsibility.” | “I’m going to address this.” | “Let’s do something else.” |
| Stabilizaton | “We’ve taken responsibility.” | “This is my problem.” | “I’m changing my ways.” |
| Expansion/Confirmation | “How well are current programs working?” | “How can I make this better?” | “What are my goals?” |
| Community Ownership | “This program is an important part of our community.” | “I’m an active participant.” | “I have a vision of something better.” |

It is your job to discover the community’s current stage and make accommodations in your project plan. Slow down and focus on raising community awareness before you consider setting up a project worksite. Or, take stock of current efforts before reinventing the wheel. Gather insight from your community members to answer the following questions taken directly from Colorado State University:

1. How much does the community know about the issue?
2. How much does the community know about the current programs and activities?
3. What is leadership’s attitude toward addressing the issue?
4. What is the community’s attitude toward addressing the issue?
5. What are the resources that are being used or could be used to address the issue?

NOTE: The Community Readiness for Community Change handbook has a survey template and instructions for successful assessment. It is available through our website at: <https://www.anawestern.org/resource-library> or on the CSU website at: <https://tec.colostate.edu/wp-content/uploads/2018/04/CR_Handbook_8-3-15.pdf>

NOTE: There is no working document for this step. Please refer to the handbook for more guidance.

Activity – Next Steps

Congratulations! At this point in the planning process, you have:

1. Affirmed your entity’s mission, vision and values on which to align your process.
2. Described your community and the people you intend to network with.
3. Determined the best outreach methods for networking with those people.
4. Connected with them personally, and then recruited, established, and hosted your steering committee.
5. Worked with your steering committee to plan for information gathering through the use of:
   1. Surveys
   2. Community Meetings
   3. Focus Groups
   4. Key Informant Interviews
6. Begun collecting and recording information as you research the needs and wants of your community.
7. Begun to analyze the results of your research and prioritize common concerns.
8. Researched secondary sources to shed additional light on these common concerns.
9. And finally, taken this information back to the community to discover their readiness to address it.

Now that you have a solid understanding of your community; you, your steering committee, and the community (through the use of more meetings, surveys, groups and interviews) can begin to identify the Products of the Planning Process – design elements that ANA recommends you develop as the foundation of the project, itself.

The ANA Project Planning and Development Manual walks your steering committee through the identification of these design elements, including: Long-term Community Goal, Current Community Condition, Project Goal, Objectives, and so on.

For now, ask your team the following questions:

1. What major themes were identified during the planning process?
2. Did any topics arise that need further community input before you begin designing the project?
3. Did you or do you need to revise your definition of the community/target audience? \_\_\_Yes \_\_\_No
4. How will you prioritize the issues, topics, or concerns in order to address just one through a project?
5. How will you avoid “reinventing the wheel” and make use of existing programs, services or resources?
6. What organizational capacity, staff structure, and expertise should you be building right now in preparation?
7. In what ways can/will you improve upon the process itself to make collecting community input easier?

NOTE: Come back to this process again and again as you begin working on ANA PPD Manual design elements.

9. Next Steps

|  |  |  |  |
| --- | --- | --- | --- |
| Action Required | Person Responsible | Start and End Dates | Comments |
| Ex. Deliver research results to Tribal Council | Steering Committee Secretary | Jan 15 | Contact Tribal Secretary by Dec 12 to get on agenda |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |