All ANA NOFO Handout

- Examples Only -

- SEDS

SEDS Outcome Tracker

| Pine Creek Co-op Outcome Tracker |
| --- |
| Long-Term Community Goal: To enjoy year-round food security in the community with access to affordable, locally grown nutritious food. |
| Current Community Condition: The community imports 95% of its produce, and the costs are the highest in the state. A community survey confirms that members are not able to purchase produce as much as they’d need to sustain healthy diets for their families. |
| Project Goal: To increase food security for community members. |
| Objective 1: By the end of the 36th month (timeframe), community members (population) will increase their purchases of locally grown food (indicator) by 50% (target). |
| Outcome | Indicator | Means of Measurement | Baseline | Project Year 1 | Project Year 2 | End of Project | 3-Yr Post |
| Increase in food security through increased accessibility of locally grown produce. | Increased purchases of affordable, locally-grown food | Percentage increase of sales transactions at weekly Farmer’s market. Community members and purchase amount information will be collected by Point of Sale software. | 0 | 15% | 35% | 50% | 60% |
| Outputs: 4 greenhouses, 8 volunteers |

SEDS Objective Work Plan

| Project Title: Pine Creek Co-op Project | Project Year: 1 |
| --- | --- |
| Project Goal: To increase food security for community members |
| Objective 1: By the end of the 36th month (timeframe), community members (population) will increase their purchases of locally grown food (indicator) by 50% (target). |
| Outcome: Increase in food security through increased accessibility of locally grown produce. |
| Activities | Outputs | Project Staff | Start Date | End Date |
| 1. Hire Agricultural Coordinator Vet job description (HR), and post Screen, interview & select candidate | Signed job offer Staff file with hiring documents (W4, benefits form, etc.) | Project Director, HR Admin Asst | 9/30/2021 | 12/30/2021 |
| 2. Initiate Community Communication Plan for Year 1 press release about award/introduce project recruitment of community participants on social media | Press Release | Project Director Communication Team | 9/30/2021 | 10/30/2021 |
| 3. Finalize MOUs with the 4 local farmers. | 4 MOUs | Project Director Agricultural Coordinator | 10/30/2021 | 11/30/2021 |
| 4. Farming Innovations Trainings a. Install and set-up greenhouse b. Install and set-up hydroponics c. Organic/Non GMO methods d. Raised bed methods e. Track produce output f. Track produce cost | Sign-in sheets Meeting Minutes | Project Director Agricultural Coordinator Admin Asst | 11/30/2021 | 07/29/2022 |
| 5. Farming Innovations Implementation a. Install and set-up greenhouse b. Install and set-up hydroponics c. Organic/Non GMO methods d. Raised bed methods | 4 greenhouses 4 hydroponic systems 4 raised bed systems Organic / Non GMO practices established | Project Director Agricultural Coordinator 4 Farmers | 12/30/2021 | 08/29/2022 |
| 6 . Recruit Greenhouse Volunteers | Ads in: Social Media Newsletter Website | Project Director Communication Team | 08/01/2022 | 9/29/2022 |
| Activities | Outputs | Project Staff | Start Date | End Date |
| ADMINISTRATIVE: Establish federal system account access and official grant file | Accounts are ready for project implementation | Project Director Financial Manager | 9/30/2021 | 10/30/2021 |
| ADMINISTRATIVE: Orientation Onboard Administrative and Project Staff – review ANA workplan, policies and procedures Meet with Partners | Signed Employee Handbooks Signed Volunteer Handbooks Handout Copies of Work Plan | All Staff | 9/30/2021 | 12/31/2021 |

- SEDS-AK

SEDS-AK Outcome Tracker

| Tribal Government Project Outcome Tracker |
| --- |
| Long-term Community Goal: Have an effective and efficient tribal government that can apply for and utilize the resources available to federally recognized tribes to meet community needs. |
| Current Community Condition: Currently, the Tribe does not have the capacity required to apply for funding and managing programs available to federally recognized tribes to meet the needs the community has regarding public health and housing; this is due to limitations of its current Internet Technology Network that is outdated and is not linked together. |
| Project Goal: Increase the capacity of the Tribal government through purchasing new computer hardware and software so that the tribal employees, and Tribal leadership are linked together with the same operating systems (Windows 10) and all employees and leadership are functioning under the newly developed IT policies and procedures. |
| Objective: At the end of 36 months (timeline), 35 (target) of the 40 tribal staff members (population), will increase their computer knowledge, skills, and efficiency (indicator) by gaining certifications in IT and will benefit from the new internet network and policies adopted by the Tribal Council. |
| Outcome | Indicator | Means of Measurement | Baseline | Project Year 1 | Project Year 2 | End of Project | 3-Yr Post Project |
| New computer operating system and policies will promote improved linkages | Increase in knowledge skills, | Pre- and post-testing of tribal employees of new operating system & policies | 0 Employees have little knowledge of new operating system | 13 Employees have enhanced knowledge | 25 Employees have enhanced knowledge | 35 Employees have enhanced knowledge | 40 Employees have enhanced knowledge |
| Outputs: 40 new computers and operational systems, 35 employee IT certificates, 4 tribal council members trained, new internet use policies created, a new server, digital telephones for tribal organization. |

SEDS-AK Objective Work Plan

| Project Title: Tribal Government Project | Project Year: 1 |
| --- | --- |
| Project Goal: Increase the capacity of the Tribal government through purchasing new computer hardware and software so that the tribal employees, and Tribal leadership are linked together with the same operating systems (Windows 10) and all employees and leadership are functioning under the newly developed IT policies and procedures. |
| Objective #1: At the end of 36 months (timeline), 35 tribal staff members (population), will increase their computer knowledge, skills, and efficiency (indicator) by 50% (target) and will benefit from the new internet network and policies adopted by the Tribal Council. |
| Outcome: New computer operating system and policies will promote improved linkages |
| Milestone Activities | Outputs | Project Staff | Start Date | End Date |
| 1. Hire and Onboard Staff | One Project Director | AOR | Oct. 2022 | Oct. 2022 |
| 2. Register the first 15 tribal staff under Cohort 1 for IT training certificate program and conduct baseline testing | Registration list Enrollment confirmation | Project Director | Nov. 2022 | April 2023 |
| 3. Purchase computers and software systems | 40 desktop computers with complete operating system | Project Director, Partner Tribe Steering Committee, Data Coordinator | Aug. 2022 | Sept. 2023 |
| 4. …… |  |  |  |  |

- P&M

P&M Outcome Tracker

| Bringing Hawaiian Home Outcome Tracker |
| --- |
| Long-term Community Goal: Every member of the Paumea’la Community will be Native Hawaiian First Language Speakers |
| Current Community Condition: There are only 8 first language speakers and 10 enrolled youth in the after-school language program, while over 35 families and 14 youth are not able to participate after school. |
| Project Goal: To take language learning out of the classroom and into the homes of Paumea’la community members. |
| Objective: By the end of year one (timeline), the Paumea’la After-School Language program (population) will adapt 3 in-classroom language curricula (target) for in-home language learning and practice to increase community-level capacity (indicator) to learn the language. |
| Outcome | Indicator | Means of Measurement | Baseline | Project Year 1 | Project Year 2 | End of Project | 3-Yr Post Project |
| Paumea’la After-School Language program will have an “increased capacity to implement [an in-home] language program.” | Increased community-level capacity to learn the language | Curriculum developed for in-home language learning and practice | 0 In-home language curricula | 3 In-home language curricula | N/A | N/A | 3 In-home language curricula |
| Outputs: 3 sets of age appropriate: training materials, exercises, workbooks, and reading materials; 1 Parent’s guide to home teaching; 1 in-home assessment tool for pre- and post-testing |

P&M Objective Work Plan

| Project Title: Bringing Hawaiian Home | Project Year: 1 |
| --- | --- |
| Project Goal: To take language learning out of the classroom and into the homes of Paumea’la community members. |
| Objective #1: By the end of year one (timeline), the Paumea’la After-School Language program (population) will adapt 3 in-classroom language curricula (target) for in-home language learning and practice to increase community-level capacity (indicator) to learn the language. |
| Outcome: Paumea’la After-School Language program will have an “increased capacity to implement [an in-home] language program.” |
| Milestone Activities | Outputs | Project Staff | Start Date | End Date |
| 1. Project Kickoff | All 4 existing staff are officially assigned to the project | AOR | Oct. 2022 | Oct. 2022 |
| 2. Conduct Assessment of in-classroom curricula | 1 documented list of updates needed and changes for in-home adaptation | Project Director | Nov. 2022 | Dec. 2023 |
| 3. Adapt Training Materials: flash cards, labels, etc. | 3 sets of Training Materials | Project Director/Language Instructor | Jan. 2023 | Mar. 2023 |
| 4. Adapt Exercises and Workbooks: revise workbooks and draft answer book for parents | 3 sets of Exercises and Workbooks | Project Director/Language Instructor | Feb. 2023 | April 2023 |
| 5. Draft Parent’s Training Guide | 1 Parent’s guide | Language Instructor and Parent Advisory Committee | Mar. 2023 | May 2023 |
| 6. ….. |  |  |  |  |

- EMI

EMI Outcome Tracker

| Our Language Is Who We Are Outcome Tracker |
| --- |
| Long-term Community Goal: All Deer Creek Potawatomi Community members will be fluent in their Native language. |
| Current Community Condition: Only 5% of Deer Creek Tribal members are fluent in our language and new learners have limited language learning resources. |
| Project Goal: Develop Potawatomi language resources specific to Deer Creek and a cadre of language speakers who are interested in becoming language instructors and leaders for the Deer Creek Potawatomi Community. |
| Objective: By the end of the 36th project month (timeline), 14 project participants between the ages of 18 to 60 years of age (population) will have attended 1800 hours of immersion language instruction with a minimum of 7 participants (50%) (target) increasing their language skills to a medium/ high level proficiency (indicator). |
| Outcome | Indicator | Means of Measurement | Baseline | Project Year 1 | Project Year 2 | End of Project | 3-Yr Post Project |
| Seven (50%) of the Deer Creek members who participate in the project will have reached medium to high levels of Potawatomi proficiency and become certificated advanced 2nd language speakers of the Deer Creek Potawatomi | Increased language skills to a medium/ high level of proficiency. | Individual language assessments of project participants will be completed twice a year. | Zero to minimal language skills | Low Medium Level | Medium Level | High Medium to High Level | High Level |
| Outputs: 14 Deer Creek member project participants will receive a minimum of 600 hours of immersion language instruction per year from a first speaker. 14 Deer Creek member project participants will complete yearly bi-annual language assessments and receive modified immersion classes to address language deficiencies and strengthen their language |

EMI Objective Work Plan

| Project Title: Our Language Is Who We Are | Project Year: 1 |
| --- | --- |
| Project Goal: Develop Potawatomi language resources specific to Deer Creek and a cadre of language speakers who are interested in becoming language instructors and leaders for the Deer Creek Potawatomi Community. |
| Objective #1: By the end of the 36th project month (timeline), 14 project participants between the ages of 18 to 60 years of age (population) will have attended 1800 hours of immersion language instruction with a minimum of 7 participants (50%) (target) increasing their language skills to a medium/high level proficiency (indicator). |
| Outcome: Seven (50%) of the Deer Creek members who participate in the Project will have reached medium to high levels of Potawatomi proficiency and become certificated advanced 2nd language speakers of the Deer Creek Potawatomi community. |
| Milestone Activities | Outputs | Project Staff | Start Date | End Date |
| 1. Advertise for and hire project director | Project director hired and provided with organizational/ project orientation | Deer Creek Band of Potawatomi Tribal Council | 9/30/2021 | 11/15/2021 |
| 2. Create project steering committee comprised of: First Speaker Instructors, Deer Creek Community Members and Partners to oversee implementation and maintain community involvement | 15-member steering committee that represents community and partners | Project Director | 11/15/2021 | 12/30/2021 |
| 3.Identify and recruit First Speaker Instructors | 3 First Language Instructors recruited | Project Director Com. Members | 10/01/2021 | 2/01/2022 |
| 4. Develop Potawatomi Language resources for oral and written communications such as a dictionary, recorded audio tapes and videos | 3 language resources developed and created: 1. Dictionary 2. Audio tapes 3. Videos | Project Director and Steering Committee | 2/15/2022 | 6/15/2022 |
| 5. Meet with speakers to develop language assessment tools | Language assessment tools and plan developed | Project Director and Language instructors | 2/16/2022 | 3/30/2022 |
| 6. Identify and recruit 14 Deer Creek members to be project participants | 14 members of the community recruited | Project Director Assistance from Steering Com. | 3/1/2022 | 5/1/2022 |
| 7. Meet with Prairie Band of Potawatomi and Hannahville Potawatomi language programs to review language structure, protocols, and materials developed by them | Review of language protocols and materials for instructional and resource development reference. | Project Director Language Instructors | 2/15/2022 | 3/30/2022 |
| 8. Complete primary language assessment of 14 project participants | Primary assessment of participants completed and on file for baseline comparisons. | Language Instructors | 4/1/2022 | 4/30/2022 |
| 9. Attend 600 hours of immersion language instruction | Increase in language skills | Language instructors, 14 participants | 4/1/2022 | 6/15/2022 |
| 10. Conduct final language assessment and evaluate the 14 project participants | Final scores documented for certification | Project Director and Language Instructors | 6/15/2022 | 7/05/2022 |
| 11. Plan for a recognition ceremony for project participants who complete the immersion language | 14 certificated Potawatomi 2nd Language Speakers | Project Director and 1st Language Instructors | 10/30/2021 | 7/30/2022 |
| 12. Establish federal system account access and official grant file. | Payment Management System access and drawdown ability established, ANA grant file created. | Project Director, Accountant | 10/30/2021 | 11/15/2021 |
| 13. Attend Post Award Training | Skills, knowledge, and reference materials obtained for proper oversight | Project Director, Accountant | 11/15/2021 | 11/30/2021 |
| 14. Complete all required ANA reports (OPR, SF-425) | All financial and programmatic reports completed on time and on file | Project Director, Accountant | 9/30/2021 | 6/30/2022 |
| 15. Attend Grantee Meeting | Knowledge of Best Practices, Networking. | Project Director and one staff member | 2/1/2022 | 2/28/2022 |
| 16. Data collection and evaluation | Data to track project progress and for ANA Annual Data Report (required administrative activity) | Project Director and Language Instructors | 9/30/2021 | 9/29/2022 |

- ERE

ERE Project Outcome Tracker

| Healthy Shellfish Subsistence Project Outcome Tracker |
| --- |
| Long-term Community Goal: Build a regional HAB monitoring program that includes analytical capacity to test local partner shellfish samples, leading to establishing effective subsistence shellfish management plans that provide accurate advisory notices to the coastal community members regarding high levels of PSTs, thus reducing the number of illnesses or deaths caused by consuming toxic shellfish. |
| Current Community Condition: Paralytic shellfish poisoning (PSP) and other marine biotoxin illnesses are on the rise in coastal Alaska communities due, in part, to climate change, thus putting subsistence shellfish harvester at greater risk of illness or death. |
| Project Goal: Develop a tribally led HAB monitoring program in coastal Alaska, that provides accurate, informative data to community subsistence harvesters to reduce the risk of PSP illnesses. |
| Objective: By the end of year 1, collect 46 phytoplankton samples per community to determine abundance of Alexandrium cells that will be used as an “early warning” to shellfish harvesters |
| Primary Outcome | Indicator | Means of Measurement | Baseline | Project Year 1 | End of Project | 3-Yr Post Project |
| Coastal partner communities will have an increased awareness of when and where Alexandrium blooms occur in the region, and how those data can be used as an “early warning” for PSP levels in shellfish. | Inform community members of Alexandrium cell densities at key harvest sites | Weekly phytoplankton data uploaded to SEATOR database and mapping tool | 0 | 322 Phytoplankton observations | 644 Phytoplankton observations | 1092 Phytoplankton observations |
| Outputs: Coastal HAB program to host annual training, sampling protocols and methods modified to fit community needs, outreach and education material disseminated in each community, phytoplankton abundance data shared with Tribal Councils and Tribal citizens. |

ERE Objective Work Plan

| Project Title: Community based Harmful Algal Blooms (HABs) monitoring to provide an “early warning” of Paralytic Shellfish Poisoning (PSP) in Coastal Alaska. | Project Year: 1 |
| --- | --- |
| Project Goal: Develop Tribally led HAB monitoring program that provides accurate, informative data to community subsistence harvesters to reduce the risk of PSP illnesses. |
| Objective #1: By the end of year 1, collect 46 phytoplankton samples per community (7) to determine abundance of Alexandrium cells that will be used as an “early warning” to shellfish harvesters. |
| Outcome: Coastal partner communities will have an increased awareness of when and where Alexandrium blooms occur in the region, and how those data can be used as an “early warning” for PSP levels in shellfish. |
| Milestone Activities | Outputs | Project Staff | Start Date | End Date |
| 1. Coastal communities will host a technical HAB workshop for partner Tribal environmental staff in Anchorage with support from O&E, NOAA’s Phytoplankton Monitoring Network. | Partner Tribes will be trained in collecting, analyzing, and reporting on abundance of Alexandrium cells | Project Director, Partner Tribe Steering Committee | Feb. 2022 | Feb. 2022 |
| 2. Collect and analyze weekly phytoplankton samples, salinity, sea surface temperature, air temperature, and environmental observations at designated shellfish harvest sites in each coastal partner community. | Tribes will input all data to Sound Toxins database where community members, researchers, and state managers can use the phytoplankton abundance data to assess potential risk of PSP event | Project Director, Data Coordinator | March 2022 | Sept. 2023 |
| 3. Develop summary of all phytoplankton observations made throughout the project year, including non-HAB species. | Summary will be used to inform Tribal Councils, researchers, and partners of phytoplankton abundance and distribution within the Coastal partner communities and determine sites for focused shellfish sampling in Year 2 | Project Director, Partner Tribe Steering Committee, Data Coordinator | Aug. 2022 | Sept. 2023 |

Sample EMI Project Outcome Tracker